## Sheet1
Team | Member | Task | June |  |  |  |  | July
|  |  | 2021-06-02 | 2021-06-09 | 2021-06-16 | 2021-06-23 | 2021-06-30 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26
Embedded Systems (ES) | Jonathan | Finish Implementing and Testing SOC Sorting Algorithm | bar: 2021-06-02 to 2021-06-30
Write SOC Estimation Algorithm
Power Module Design (PMD) | Andrew | Learn Ansys
| Hiromi | Redesign VIAs and footprints for Current Sense | bar: 2021-06-02
| Andrew & Hiromi | Learn more about designing PCBs on OrCad | bar: 2021-06-02 to 2021-06-30
Finish Current Sense PCB Board | bar: 2021-06-02 to 2021-06-16